# DEFINE PHASE REPORT — project_001

# Problem Statement

A/R is part of cashflow performance. In 2016, 36.20% of total A/R overdue in ID03 was triggered by PT Smart, so we will focus on this customer for this project. High A/R overdue shows that a company is selling its product to customers on credit and taking longer to collect money. It means the company has less readily available cash to finance operations. In addition, high A/R overdue will block orders, and CSD cannot send the product until the payment has been made by PT Smart.

# Goal Statement

Reduce monthly overdue A/R for PT Smart to 11% by the end of Nov 2017.

# Business Case

Reducing the overdue A/R percentage for PT Smart will improve cash flow, reduce blocked orders, and enhance operational efficiency, ultimately reducing costs and improving financial performance.

# Scope

In Scope  : Accounts receivable processes, Credit policy review and adjustments, Training and development for the finance team, DN and GI process by the logistics team

Out Scope : Non-financial customer service issues, Supplier management outside of A/R impact

# CTQ List

- A/R Overdue Percentage (Percentage %)

- The percentage of total accounts receivable that is overdue for PT Smart.

- Days Sales Outstanding (DSO) (Days days)

- The average number of days it takes PT Smart to pay its invoices.

- Blocked Orders Due to Overdue A/R (Count orders)

- The number of orders blocked because PT Smart has overdue accounts receivable.

# Y Variable

A/R Overdue Percentage

# X Categories (6M)

Man: Training for accounts receivable team on collection strategies, Staffing levels in the finance department

Machine: Accounts receivable management software, Automated reminders for overdue payments

Method: Credit policies and terms for PT Smart, Collection process standard operating procedures

Material: Quality of customer credit evaluations, Documentation for credit terms and agreements

Measurement: Regular monitoring of A/R overdue percentages, Tracking of DSO and blocked orders

Environment: Economic conditions affecting customer payments, Market trends impacting cash flow

# SIPOC

Suppliers: Customer credit evaluation agencies, Financial software providers

Inputs   : Customer credit evaluations, Accounts receivable data, Credit policies

Process  : Credit approval process, Invoice generation and tracking, Payment collection

Outputs  : Reduced A/R overdue percentage, Improved cash flow

Customers: Finance department, Operations team

# Early Measurement Plan

Measures   : Monitor A/R overdue percentage monthly, Track DSO and blocked orders bi-weekly, Review credit policies quarterly

Responsible: Finance Management Team

# Risk & Project Type

Risk Level   : Medium

Project Type : Process Improvement

# Agent Insight

- The primary CTQ, "A/R Overdue Percentage," is selected due to its direct impact on cash flow and operational efficiency, aligning with the project's goal to reduce overdue A/R for PT Smart.
- The scope is focused on accounts receivable processes and credit policy adjustments, ensuring a targeted approach to address the high A/R overdue issue.
- Key risks include potential resistance to process changes and economic conditions affecting customer payments; assumptions include the availability of accurate A/R data and effective training for the finance team.
- Past successful audits in similar contexts highlight the importance of robust credit evaluation and consistent monitoring of overdue percentages.
- Leverage automated reminders and management software to streamline the collection process, as evidenced by previous projects.
- Next steps for Measure: 
  1. Collect and analyze baseline data on A/R overdue percentages and DSO for PT Smart.
  2. Develop a detailed data collection plan ensuring accuracy and consistency in tracking overdue payments and blocked orders.
  3. Engage with the finance team to validate data sources and ensure alignment on measurement criteria.